SPECIFICATION NO: xxxx

12000 Jefferson Avenue

Newport News, VA 23606

| TITLE: CLAS12 / HallB Region 1 Drift Chamber Assembly Statement of Work WBS xxxxx | DATE: xxxxxxx |
| --- | --- |
| BY: Mac Mestayer |  |
| APP: ________________ ____________ Mac Mestayer Date SOTR | APP: __________________ ____________ Volker Burkert Date Hall B Group Leader |
|  | APP: _________________ ____________ Latifa Elouadrhiri Date CLAS12 Project Mgr. |
|  | APP: _________________ ____________ Glenn Young Date APM for Physics |

| _ |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| REV | ECO# | DESCRIPTION | BY | CHK. | APP. | APP. | DATE |

Table of Contents

1.0	Scope of Work and Required Content of Proposal	3

2.0	Requirements	7

3.0	Quality Assurance	8

4.0	Testing,  Tracking and Changes to the Contract	98

5.0	Storage and Delivery	910

6.0	Milestones	10

10

7.0	Applicable Documents	1110

# Scope of Work and Required Content of Proposal

This Statement of Work (SOW) defines the scope of work for the stringing, instrumentation and delivery of six  Region 1 Drift chambers for the CLAS12 detector at Jefferson Lab. The construction of the Region 1 Drift Chambers (R1DC) is vital to the success of the CLAS12 detector at Jefferson Lab (JLab).  This project represents a significant effort and is planned as a joint venture between Idaho State University (ISU) and JSA/Jefferson Lab (JLab), consistent with the intent of the Memorandum of Understanding dated xxxxxxx and subsequently fully executed Subcontract.  This SOW is part of a Request for a Proposal from ISU and defines the scope of work to be done and establishes the required contents of a proposal document.

  - General Description of the Project

The R1DC project consists of the stringing and instrumentation of six “Region 1” drift chambers.  JLab has designed and procured all parts necessary for this work.  Jlab will assemble the chambers boxes and ship them to ISU.  ISU will string, instrument and test the six chambers and ship them back to Jlab.

Each chamber has a trapezoidal box shape consisting of four rigid sides, with thin Mylar foils on the two remaining sides, providing a sealed gas volume.  Two of the rigid sides are called “endplates” and are each penetrated by approximately 5,000 precision holes in which will be placed the “feedthroughs” and “crimp pins” used to affix the ends of the chamber wires.

The building of the six boxes at Jlab will require bolting of the two endplates to the remaining rigid plates, the “nose” and “back” plate assemblies, to form an open box.  Feedthroughs will be inserted and glued into the endplates by JLab.  After the boxes are assembled, they will be shipped to ISU and then “stringing” of the wires will proceed.  After all wires are strung and tested for tension and continuity, the wire positions will be surveyed.  The Mylar foil “gas bags” will then be installed, followed by installation of the on-chamber electronics boards.  The chamber will then be tested for operational functionality, packaged and delivered to JLab for installation and final commissioning.

The effort to string and instrument the R1DC’s will be performed by a combination of contributed labor from ISU’s staff as outlined in the MOU(1),  and temporary manpower hired specifically for this project.

  - Work to be Performed by ISU:

    - In coordination with JLab, ISU shall prepare and maintain a cleanroom suitable for the stringing of the R1DC’s and prepare a safe environment for any testing of the R1DC.

    - Coordinate the hiring, training, supervision and payment of all  (even the lead stringer?) temporary manpower used in R1DC stringing, instrumentation and testing.

    - Purchase all consumables used during assembly, including glue and cleanroom supplies.

    - Clean  and visually inspect all parts received from JLab for this project for possible damage and report any nonconformance to JLab.  Record part identification and number received.

    - String, instrument, and test the chambers.  See the referenced document, “Stringing Procedures for CLAS12 Drift Chambers”  for a more detailed description of the procedures to be followed in stringing a chamber.

The sub-activities include the following:

      - Set up the chamber-handling fixtures in the cleanroom.

      - Perform all necessary handling of the chambers from removing the chamber and attaching a strong-back from the delivery truck and moving this assembly into the cleanroom, followed by installation on the “stringing fixture” itself and thereafter performing any rotations necessary for the following tasks.

      - Set up the “stinging machine” on the upper part of the stringing fixture.  Commission the machine and train the operators so that efficient (what does efficient mean? # of time we rethread it /hr?)  de-spooling of the wire is enabled.

      - String the roughly 5,000 wires per chamber.  This sub-task will consist of the following: affixing a weight to the end of the wire, inserting the weighted end through the upper feedthrough, de-spooling the wire and guiding it through the lower feedthrough.  The upper operator will then cut and crimp (do we first crimp and then cut?)  the wire and insert the crimp pin into the upper feedthrough.  The lower operator will tension, crimp and affix the wire in the bottom feedthrough. The integrity of the wires will be tested for proper tension and electrical connectivity (refer to section 4.1 here?).

      - Insert glue to affix the crimp pin to the feedthrough, and insert additional glue into the open end of the crimp pins and install the “gas bags” to provide a leak-tight gas volume.

      - Supervise the survey of the chamber. (200 micron at ISU one or a survey at JLab?)

      - Install the on-chamber electronics boards and necessary test cables.

      - Flow operating gas through the chamber.

      - Test the chamber for operational functionality and good signal quality.

    - Perform any additional tests of the completed R1DC’s in accordance with the approved  acceptance test plan.

    - Keep careful records of all operations in a manner convenient for quality assurance assessment purposes.

    - Arrange for transportation of the completed chambers from ISU to Jefferson Lab in a safe manner that provides reasonable assurance that material will not be damaged in transit.

    - Recommend improvements to the assembly process with increased experience.

  - Adherence to Overall Schedule

The R1DC project must fit within the schedule constraints of the overall CLAS12 upgrade project.  This is reflected in the Milestones, see Section 6.0. The overall work plan submitted should be consistent with the submitted budget and the project duration specified in the Milestones.

  - Deliverable to JLAB

The estimated milestones for the project are listed in Section 6.0.  ISU must submit a proposal as described in Section 1.0 with proposed milestones and other plans as noted herein.  Following approval, ISU will use reasonable efforts to string and test the drift chambers in accordance with the JLab-supplied stringing procedures document (see footnote 2, as may be modified by mutual agreement of the parties) and deliver the completed chambers to JLab. Monthly reports are to be submitted on progress of assembly relative to the baseline schedule and cost for input to the project Earned Value Management System.

  - JLAB supplied materials, services and equipment

    - JLab will supply assembled chamber boxes, ready for stringing..

    - JLab will supply crimp pins for affixing the wire.

    - JLab will supply all wire needed.

    - JLab will supply a wire tension tester.

    - JLab will supply all circuit boards, as well as crimp pins to circuit board connecting material and buss wire with which to wire-wrap the field and guard wires.

    - JLab will provide all assembly fixtures: strong-backs, stringing fixture and man-lifts necessary to handle the chamber bodies.

    - JLab will provide the stringing de-spooler and crimping machines.

    - JLab will provide the assembly-drawing package for all the parts that are to be assembled.

    - JLab will maintain a document with detailed stringing procedures.

    - JLab will provide engineering consultation, advice and support as required for the assembly of any fixtures.

    - JLab will provide other small parts that are more cost-effective to be supplied by JLab.

    - JLab will supply any replacement parts for nonconforming parts as identified by ISU as noted under 1.2.d

  - ISU supplied materials, services and equipment

    - An assembly manager (assembly manager is synonymous with lead stringer?) to oversee all aspects of construction.

    - All supervisory, hiring, training and procurement labor, except that training which is planned to take place at Jlab.

    - Procurement  of all consumables, machinery, tools & facilities used in the course of assembly and not listed in section 1.5.

    - A clean room suitable for stringing, instrumenting and testing of the R1DC’s.

    - Crane facilities adequate for loading and handling of chambers and fixtures delivered from or to JLab.

    - Preparation for periodic progress reviews attended by the CLAS12 liaison and the ISU assembly manager to be scheduled as needed at JLab’s direction.  Such reviews will examine all aspects of assembly and stringing including, but not limited to, summaries of assembly and testing, description of any technical issues encountered during material preparation, assembly and testing, and comparison of measured performance relative to relevant specifications. A written summary of progress is part of this preparation.

    - Monthly reports on progress of assembly relative to the baseline schedule and cost for input to the project Earned Value Management System.

    - A Draft Assembly Plan and a Draft Acceptance Test Plan to be submitted as part of the proposal and formally evaluated by JLab prior to contract award. ISU should not proceed with stringing without JLab confirmation.

    - A Final Assembly Plan and Final Acceptance Test Plan and Quality Assurance Plan, presented at a JLab-convened review within 90 days of contract award, for JLab approval.

  - Items to be Contained in the Proposal

    - Description of the ISU clean room to document that it is suitable for the stringing of the R1DC’s.

    - Designation of a R1DC assembly manager as one of the key personnel to supervise stringing and instrumentation of the R1DC’s and provide formal supervision of the labor associated with the R1DC assembly.

    - An Assembly Plan that will address logistics issues, including but not limited to, the following: shift crew size, sample daily work plans, sample daily quality-assurance work plans, and contingency plans in the event of equipment malfunctions and personnel sickness.

    - A Schedule consistent with the JLab-supplied estimated project milestones (see Section 6.0) with the estimated level of effort and with the planned crew size.

    - A Budget consistent with the estimated duration, level of effort and anticipated crew size as specified in the Assembly Plan and Schedule.

    - A Quality Assurance Plan that describes the tests and procedures that ISU will use to ensure that the R1DC’s will be able to perform in a manner consistent with the research mission for the CLAS12 detector.

    - An Acceptance Test Plan for testing the completed R1DC’s.

    - A Shipping and Storage Plan (see Section 5.0 for more details).

# Requirements

  - Inspection

ISU will perform tests to determine whether it believes the R1DC’s will be adequate for the CLAS12 research mission and report the findings to JLab as part of the Acceptance Test Plan (Section 1.7g)

  - Conflicts

Any and all inconsistencies or discrepancies regarding the drawings, specifications or procedures are to be brought to the attention of JLab for resolution prior to the commencement or continuation of work.

  - Marking

The intended sector location of the final R1DC’s should be visible after assembly.

  - Materials

The materials shall be as specified in the drawings or in the attached document, “Stringing Procedures for CLAS12 Drift Chambers” (see footnote 2).

# Quality Assurance

ISU shall prepare a quality assurance plan as part of the proposal (see Section 1.7f) and shall furnish such documentation as JLab may require throughout the assembly process.  ISU shall conduct quality control procedures and tests in an effort to ensure that the R1DC’s performance capabilities are consistent with the CLAS12 research mission.

This plan shall contain (when applicable) the mechanism for:

- Inspection of all materials received from suppliers or from JLab and the recording of this information. This includes in particular the wire spools, crimp pins, feedthroughs and circuit boards.

- Obtaining and recording of relevant material certifications and analyses as necessary.

- The calibration and identification of standards and instrumentation used; the intervals between calibrations are also to be defined.

- Establishment of inspection points during the production process, when critical parameters will be measured.

- The recording of all inspection data in such a manner so that the history of an item can be readily traced.

- The sharing with JLab of all data related to the above.

# Testing,  Tracking and Changes to the Contract

  - Testing: ISU shall include an Acceptance Test Plan (see Section 1.7g) with their contract proposal, which must be approved by JLab. The plan must include test procedures during critical stages of assembly to measure the electrical and mechanical integrity of all wires. In particular, the continuity and wire tension must be tested for all wires.  The final test before delivery will be the observation of a suitable signal on each of the sense wires.  For this purpose the chamber must have electronics boards installed, must have proper voltages delivered to the circuit boards, and must be filled with the appropriate gas mixture.

  - Tracking: Reports must be sent to JLab on the following items:

      - Electrical continuity tests of all wires.

      - Tension measurements of all wires.

      - Gas tightness of the R1DC volumes (gas pressure).

      - Detector signal tests at operating voltages.

These tests are further described in the referenced document, “Stringing Procedures for CLAS12 Drift Chambers.”  Reporting plans must be included in the Quality Assurance (see sec.1.7f )  part of the proposal.

  - Change to the contract: Procedures for making changes:

Consistent with the intent of the Memorandum of Understanding dated xxxxx and not withstanding anything to the contrary in a subsequent Subcontract, the parties understand and agree that the R1DC’s are experimental equipment and that the parties are performing the work under this Subcontract on a best effort basis.  If the R1DC’s assembled by ISU do not perform in accordance with the goals set forth in the drawings and specifications and/or ISU is not able to complete the assembly of the R1DC’s within the proposed milestone schedule, and reasonable best efforts have been applied, the parties will discuss alternative courses of action.  Such alternatives could include without limitation, modification of the proposed R1DC drawings or specifications or an extension of the Subcontract.

# Storage and Delivery

ISU will perform all tasks necessary for the safe storage of the completed or partially completed chambers while at ISU, including but not limited to the following: maintaining a clean space with temperature and humidity control.  Specific guidance on these requirements is included in the referenced document, “Stringing Procedures for CLAS12 Drift Chambers.”

ISU will perform all tasks necessary for the safe delivery of the completed chambers to JLab, including but not limited to the following:

- Negotiate the contract with an appropriate shipping company; specifying internal temperature control sufficient to avoid unacceptable temperature-related stress.  Similarly, specify driving procedures and equipment to minimize gravitational shock loading from, e.g., rough roads.

- Design and fabricate or purchase a suitable system for minimizing gravitational shock loading on the chambers while in transit.

- Arrange for the move of the chambers from the cleanroom into the truck.

# Milestones

  - Determining the Baseline Schedule and Work Plan

The proposed assembly schedule of the CLAS12 Region 1 Drift Chambers is tied to the overall schedule of the JLab 12 GeV Upgrade project. Please refer to Table 1 (below) for details.  The JLab-convened “Readiness Review” will take place within three months of the contract award.

Table 1. Deliverables and Milestones

| Activity | Expected Milestone | Estimated Date |
| --- | --- | --- |
| Readiness Review | Production start | 2/15/11 |
| Begin stringing chamber #1 | Stringing begins at ISU | 3/15/11 |
| Finish stringing, instrumentation and testing of chamber #1 | R1DC#1 complete | 07/31/11 |
|  | R1DC#2 complete | 11/30/11 |
|  | R1DC#3 complete | 3/31/12 |
|  | R1DC#4 complete | 6/30/12 |
|  | R1DC#5 complete | 09/30/12 |
|  | R1DC#6 complete | 12/30/12 |
| Delivery of all sixR1DC’s to Jlab | Project complete | 03/15/13 |

Changes to the Baseline Schedule

Any delays or unexpected circumstances must be reported immediately to the Hall B liaison and engineer in order to develop a mitigation plan.

# Applicable Documents

  - Drawings

Jefferson Lab will provide drawings of the chamber body assembly, the stringing fixture, the strong-back and the stringing machine to assist in their proper use and maintenance.

  - Parts Specifications

Jefferson Lab will provide Hall B wire, feedthrough, crimp pin, endplate and assembly fixture specifications to assist in their proper use.

  - Procedural Specifications

The Hall B stringing procedures document specifies procedures and requirements for all aspects of the work as described in section 1.2e (see “Stringing Procedures for CLAS12 Drift Chambers,” referenced as footnote 2 in this document).

  - Change Requests

Because of the experimental nature of the R1DC’s, the parties understand and agree that they may alter the drawings and specifications as necessary during the term of the project.  Such modifications will be by mutual agreement of both parties.

Memorandum of Understanding between JSA,LLC, Thomas Jefferson National Accelerator Facility and ISU of xxxxxx, regarding work for the CLAS12 project.

http://clasweb.jlab.org/drawings/CLAS12/DRIFT_CHAMBERS/clas12-R2-stringing-manual-draft-5-6-10.doc

Latifa to send a copy 4/2/2010

I agree - Mac

Who will be billed for temporary manpower?  Is this part of the funding allocated for this subcontract or is it extra?  Suggest adding language “…hiring, training, supervision, and payment of all temporary…”

ISU will pay for the temporary labor, and will subsequently bill us through this subcontract.  This is funded, and is in fact the major expense item. - Mac

Glue specifications?

Steve, could you provide the glue specifications? - Mac

We do not use a “specification” for the glue per se. We only specify the glue that must be used.-Steve

Need a copy of these Procedures

Will send the procedure today.-Steve

Steve, could you get a copy of George’s procedures? - Mac

Does ISU know what information is required?  Do we have a sample record we can provide?

We are working out the procedures now with ISU.  We will have a sample record by the time of the readiness review. - Mac

agree - Mac

agree - Mac

Suggest this be deleted or changed.  While it is experimental work, a certain level of quality should be expected.  Also, the sole source justification indicates that this is a critical path item and that it is vital that ISU finish on time.

I agree; “best effort” says it all -Mac

Are shipping costs part of this contract?

Yes, shipping costs are part of the contract. -Mac

ISU needs to do this?

Is this timing still reasonable?

Yes, we still think this is achievable. - Mac

Need copy of these specifications.

The specifications for the endplates, boxes and fixtures are contained in the drawings of those parts. I will email the specifications for the wire, feedthroughs and crimp pins to you today. -Steve

Steve, could you get these documents? - Mac